ML Research Project Proposal

Beyond the Tumor: Integrating Transcriptomic Dysregulation and Immune Signatures for Survival Prediction in Lung Adenocarcinoma

A Multi-Modal Machine Learning Approach

Prepared by:

Student 1: Sonica (Bioinformatics Lead) |  Student 2: Parth (ML Lead)

Datasets: TCGA-LUAD · GTEx · GEO · CPTAC-LUAD

Target Journals: Briefings in Bioinformatics · PLOS Computational Biology (TBC)

Timeline: 1.5 Months Initial Implementation

# 1. Introduction & Background

Lung adenocarcinoma (LUAD) is the most common subtype of non-small cell lung cancer and remains one of the leading causes of cancer-related death worldwide. Despite improvements in targeted therapies and immunotherapy, patient outcomes remain highly variable — two patients with the same stage and treatment can have dramatically different survival outcomes.

Most current survival prediction models look at tumor gene expression in isolation: how active are genes inside the tumor? But this approach misses two crucial biological realities:

- Tumors do not arise in a vacuum. They develop from normal tissue, and how far a tumor has strayed from healthy lung biology may matter just as much as the tumor's expression profile itself.

- The immune system is a key determinant of cancer outcome. Whether the immune system can recognize and fight the tumor depends on the tumor's altered biology — and this interaction is not captured by tumor-only models.

This project proposes to combine three streams of biological information — tumor gene expression, tumor-normal transcriptomic dysregulation, and immune microenvironment profiles — into a single multi-modal machine learning model to predict survival in LUAD patients.

# 2. Why This Problem Matters Clinically

Lung cancer is responsible for more deaths than breast, colon, and prostate cancers combined. In LUAD specifically:

- 5-year survival rates remain below 25% across all stages.

- Immunotherapy (e.g. anti-PD-1/PD-L1) works for some patients but fails in others, and we still cannot reliably predict who will benefit.

- Existing prognostic tools (TNM staging, EGFR mutation status) are insufficient — two stage III patients may have survival times differing by years.

A better survival prediction model could help clinicians make more informed treatment decisions, identify patients who are most likely to benefit from immunotherapy, and stratify patients for clinical trials. This is not just a computational exercise — it has real potential clinical impact.

# 3. Current Research Gaps

| Gap | Why It Matters |
| --- | --- |
| Most ML survival models use tumor expression alone | Ignores how far the tumor has deviated from healthy baseline |
| Immune profiling studies rarely integrate dysregulation scores | Misses the biological link between tumor alteration and immune recognition |
| Many models lack external validation | Cannot assess generalizability; results may be dataset-specific |
| Deep learning models often lack biological interpretability | Clinicians cannot trust or use a black-box prediction |
| Tumor-immune interaction modelled separately, not jointly | The interaction between deviation and immune response is the key signal |

# 4. Novelty of This Project

What makes this project different from existing work: The central novelty is the tumor-normal dysregulation score — a per-patient, per-gene quantification of how much each tumor's expression deviates from healthy lung tissue (using GTEx normals). This dysregulation signal is then combined with immune cell fraction estimates and tumor expression in a multi-modal survival model, allowing us to ask: does the degree of biological deviation shape the immune response, and does that interaction predict survival better than any single input alone?

- Dysregulation score as structured input — not just raw expression, but deviation from normality.

- Multi-modal fusion — combining three biologically distinct signals in one model.

- Interpretability focus — SHAP values to identify which dysregulated genes and immune interactions drive predictions.

- External validation — held-out GEO and CPTAC cohorts to test generalizability.

# 5. Main Research Question

Core Question: Can patient-specific tumor-normal transcriptomic dysregulation, combined with immune microenvironment signatures, improve survival prediction in Lung Adenocarcinoma compared to models using tumor gene expression alone?

# 6. Hypothesis

Hypothesis (plain language): We hypothesize that patients whose tumors show greater deviation from healthy lung tissue biology, particularly in genes related to immune recognition and cellular stress, will have a distinct immune microenvironment — and that combining these two signals will predict survival more accurately than using tumor expression alone. In short: how different the tumor is from normal tissue, and how the immune system reacts to that difference, together determine survival better than either signal alone.

# 7. Research Aims & Objectives

Aim 1 — Compute Tumor-Normal Dysregulation Scores

- Download and preprocess TCGA-LUAD tumor RNA-seq and GTEx healthy lung RNA-seq.

- Compute per-patient, per-gene dysregulation scores (z-score of tumor expression relative to healthy distribution).

- Identify the top dysregulated gene sets and annotate with pathway information.

Aim 2 — Profile the Immune Microenvironment

- Run CIBERSORT or TIMER2.0 on TCGA-LUAD samples to estimate immune cell fractions (CD8+ T cells, Tregs, NK cells, macrophage subtypes, etc.).

- Compute ssGSEA immune gene set enrichment scores as a complementary immune signature.

- Correlate immune profiles with dysregulation scores to test biological coherence.

Aim 3 — Build and Compare Survival Prediction Models

- Baseline: Cox Proportional Hazards model using clinical variables only.

- Univariate models: Cox-Lasso with tumor expression / dysregulation / immune features separately.

- Multi-modal model: DeepSurv or Attention-based fusion model combining all three streams.

- Evaluate models using concordance index (C-index), time-dependent AUC, and calibration curves.

Aim 4 — Interpret and Validate

- Apply SHAP values to identify biologically meaningful features driving survival predictions.

- Validate top findings in independent GEO and CPTAC-LUAD cohorts.

- Map top SHAP features to known cancer biology (immune evasion, EMT, MHC-I loss, etc.).

# 8. Simplified Biological Explanation (For the ML Student)

What is a tumor doing differently from a normal lung cell?

Every cell in your body runs on gene expression — genes being switched on or off to perform their function. A healthy lung cell has a characteristic pattern: some genes are very active, others are quiet. When a cell becomes cancerous, this pattern gets disrupted. Some genes that should be quiet become loud (oncogenes), and some that should be loud get silenced (tumor suppressors).

We measure this disruption by comparing each patient's tumor expression to a reference distribution of healthy lung tissue (from the GTEx database). The result is a dysregulation score — essentially: for each gene in each patient, how far has this gene's activity shifted from what you'd see in a healthy person?

Why does the immune system matter?

The immune system is supposed to recognize and destroy abnormal cells — including cancer cells. It does this by detecting molecular signals that cancer cells display on their surface. But tumors can hide from the immune system (immune evasion) or suppress it. The degree to which this happens — measured by the types and activity levels of immune cells infiltrating the tumor — strongly affects whether the patient survives.

Why combine them?

A tumor that is highly dysregulated might be more visible to the immune system (lots of strange proteins to detect) — or it might have evolved mechanisms to hide better. By combining the dysregulation score with the immune profile, we can model this interaction rather than guessing at it. This is the core biological bet of the project.

# 9. Simplified ML Explanation (For the Biology Student)

What are we predicting?

We are predicting patient survival using a technique called survival analysis — specifically, we want to predict how long a patient is likely to survive after diagnosis, taking into account that some patients are still alive at the end of the study (these are called 'censored' observations and require special statistical handling).

What is a Cox model?

The Cox Proportional Hazards model is the standard statistical tool in medicine for survival analysis. It estimates how much each variable (e.g. a gene's expression level) increases or decreases the risk of death. It is transparent and interpretable — which is why we use it as our baseline before moving to deep learning.

What is DeepSurv?

DeepSurv is a deep learning version of the Cox model — it uses a neural network to learn non-linear relationships between features and survival risk. It is well-suited to high-dimensional data like gene expression, where relationships are complex and non-linear.

What is the multi-modal fusion model?

Instead of feeding all data into one model, we build separate encoders for each data type (tumor expression, dysregulation scores, immune features), then fuse them at a middle layer. This allows each stream to be processed in a way appropriate to its biology before being combined. An attention mechanism can then learn which stream matters most for each patient.

# 10. Experimental Design & Workflow

Overall Pipeline (Text Diagram)

| Step | Input | Process | Output |
| --- | --- | --- | --- |
| 1 | TCGA-LUAD + GTEx | Preprocessing & normalization | Cleaned expression matrices |
| 2 | Normalized matrices | Per-gene z-score vs GTEx | Dysregulation score matrix (patients × genes) |
| 3 | TCGA-LUAD expression | CIBERSORT / ssGSEA | Immune cell fraction matrix |
| 4 | Clinical data | Curate OS, PFS, stage, age, sex, smoking | Clinical feature matrix |
| 5 | All matrices | Feature selection + integration | Multi-modal input tensors |
| 6 | Tensors + survival labels | Cox baseline → DeepSurv → Fusion model | Survival predictions |
| 7 | Predictions + true survival | C-index, AUC, calibration | Model performance table |
| 8 | Best model | SHAP analysis | Feature importance rankings |
| 9 | Top features | GEO + CPTAC validation | Externally validated gene signatures |

# 11. Data Sources & Sample Sizes

| Dataset | Role | Approx. N | Access |
| --- | --- | --- | --- |
| TCGA-LUAD | Primary training cohort | ~500 tumors | GDC Data Portal (free) |
| GTEx Lung | Healthy tissue reference for dysregulation | ~400 normals | GTEx Portal (free) |
| GEO (e.g. GSE72094) | External validation cohort 1 | ~400 LUAD | GEO NCBI (free) |
| CPTAC-LUAD | External validation cohort 2 | ~110 tumors | PDC Portal (free) |
| Held-out TCGA split | Internal test set | ~100 tumors | From TCGA (20% hold-out) |

# 12. Detailed Step-by-Step Pipeline

Phase 1: Data Acquisition & Preprocessing (Biology Student — R)

- Download TCGA-LUAD RNA-seq HTSeq counts and clinical data from GDC Portal using TCGAbiolinks.

- Download GTEx v8 Lung gene TPMs from GTEx Portal.

- Normalize both datasets to log2(TPM+1). Apply quantile normalization to make them comparable.

- Filter to protein-coding genes present in both datasets (~17,000 genes).

- Remove samples with missing survival data. Document exclusion criteria clearly.

- Curate survival endpoints: Overall Survival (OS) in days, vital status (dead/alive).

Phase 2: Dysregulation Score Computation (Biology Student — R)

- For each gene, compute mean and standard deviation of expression across GTEx lung samples.

- For each TCGA-LUAD tumor sample, compute a z-score: (tumor expression - GTEx mean) / GTEx SD.

- This gives a matrix of size [patients × genes] representing how much each gene deviates.

- Filter to top 5,000 most variable dysregulation genes to reduce dimensionality.

- Run pathway enrichment on highly dysregulated genes (clusterProfiler, KEGG/Hallmark MSigDB).

Phase 3: Immune Profiling (Biology Student — R + web tools)

- Submit TCGA-LUAD expression matrix to CIBERSORT web tool to get 22 immune cell fractions per sample.

- Run ssGSEA in R using GSVA package with immune-related Hallmark gene sets (e.g. IFN-gamma response, TNF-alpha signaling, IL-2/STAT5).

- Also extract ESTIMATE immune/stromal scores as additional features.

- Perform correlation analysis: which immune cells correlate with which dysregulation patterns?

Phase 4: Feature Engineering & Integration (Both Students)

- Select top dysregulation features using univariate Cox regression p-values (FDR < 0.05).

- Scale all features to [0,1] range. Save scalers for application to validation cohorts.

- Assemble final input tensors: [tumor expression | dysregulation scores | immune features | clinical].

- Split TCGA data: 70% train / 10% validation / 20% test. Stratify by survival event rate.

Phase 5: Modelling (ML Student — Python/PyTorch)

- Model 1 — Cox-Lasso: clinical variables only (baseline).

- Model 2 — Cox-Lasso: tumor expression features.

- Model 3 — Cox-Lasso: dysregulation features only.

- Model 4 — Cox-Lasso: immune features only.

- Model 5 — DeepSurv: all features concatenated (single stream).

- Model 6 — Multi-modal fusion: separate encoders per stream, late fusion with attention.

  - Encoder: 2-layer MLP per stream (64 → 32 units, ReLU, dropout 0.3).

  - Fusion: concatenate encoded representations, pass through shared 32-unit layer.

  - Output: risk score (scalar), trained with negative log partial likelihood loss.

  - Attention: learn a weight per stream per patient to identify dominant signal.

Phase 6: Evaluation & Interpretation (Both Students)

- Primary metric: Concordance Index (C-index). Target > 0.65 for publication.

- Secondary: time-dependent AUC at 1, 3, 5 years; Brier score (calibration).

- Apply SHAP (SHapley Additive exPlanations) on the best model to rank feature contributions.

- Map top 50 SHAP features to biological pathways and literature.

- Apply best model to GEO and CPTAC cohorts. Report C-index and AUC in validation.

# 13. Tools, Software & Packages

| Task | Tool / Package | Language | Who Uses It |
| --- | --- | --- | --- |
| TCGA data download | TCGAbiolinks | R | Biology Student |
| Expression normalization | edgeR, limma | R | Biology Student |
| Dysregulation z-scores | Custom script | R | Biology Student |
| Pathway enrichment | clusterProfiler, msigdbr | R | Biology Student |
| Immune deconvolution | CIBERSORT (web), TIMER2.0 | Web tool | Biology Student |
| ssGSEA scores | GSVA package | R | Biology Student |
| ESTIMATE scores | estimate R package | R | Biology Student |
| Survival analysis (baseline) | survival, survminer | R | Biology Student |
| Cox-Lasso | glmnet | R | Biology Student |
| DeepSurv / fusion model | PyTorch, pycox | Python | ML Student (Parth) |
| SHAP analysis | shap library | Python | ML Student (Parth) |
| C-index, AUC evaluation | lifelines, scikit-survival | Python | ML Student (Parth) |
| Data wrangling | pandas, numpy | Python | ML Student (Parth) |
| Visualizations | matplotlib, seaborn, ggplot2 | Python/R | Both |
| Version control | Git + GitHub | — | Both |

# 14. Task Division Between Students

| Task | Biology Student | ML Student (Parth) |
| --- | --- | --- |
| Data download & cleaning | ✅ Primary | Support |
| GTEx normalization | ✅ Primary | — |
| Dysregulation z-score computation | ✅ Primary | — |
| Pathway enrichment analysis | ✅ Primary | — |
| Immune deconvolution (CIBERSORT) | ✅ Primary | — |
| ssGSEA immune signatures | ✅ Primary | — |
| Clinical feature curation | ✅ Primary | — |
| Cox-Lasso baseline models | ✅ Primary | Support |
| Feature export to Python | ✅ Primary | — |
| DeepSurv implementation | — | ✅ Primary |
| Multi-modal fusion architecture | — | ✅ Primary |
| Training, tuning, evaluation | — | ✅ Primary |
| SHAP analysis | Support (interpretation) | ✅ Primary (coding) |
| Biological interpretation of SHAP | ✅ Primary | Support |
| External validation pipeline | Data prep (R) | ✅ Model application (Python) |
| Figure generation | R plots | Python plots |
| Writing — biological sections | ✅ Primary | — |
| Writing — methods/ML sections | Support | ✅ Primary |

# 15. Week-by-Week Timeline (6 Weeks / ~1.5 Months)

| Week | Biology Student Tasks | ML Student (Parth) Tasks | Joint Milestone |
| --- | --- | --- | --- |
| Week 1 | Download TCGA-LUAD + GTEx, normalize, QC, filter, curate survival data | Set up Python environment, explore processed data, review survival modelling (pycox docs) | Clean data matrix ready; shared GitHub repo set up |
| Week 2 | Compute dysregulation z-score matrix; run pathway enrichment; select top features | Implement Cox-Lasso in Python using glmnet-equivalent; test on expression features | Dysregulation matrix finalized; baseline Cox model running |
| Week 3 | Run CIBERSORT + ssGSEA; correlate immune profiles with dysregulation | Implement DeepSurv; evaluate on expression-only and dysregulation-only inputs | Immune features ready; DeepSurv baseline C-index computed |
| Week 4 | Assemble final multi-modal feature matrix; prepare GEO validation cohort | Build multi-modal fusion architecture; train and tune; compare all models | All models trained; C-index comparison table generated |
| Week 5 | Interpret SHAP features biologically; map to pathways; apply to CPTAC | Run SHAP analysis; apply best model to GEO + CPTAC; compute validation metrics | External validation done; SHAP feature list finalized |
| Week 6 | Write biological introduction, methods, results narrative; generate R figures | Write ML methods, model architecture description; generate Python figures | Full draft circulated; figures complete; ready for supervisor review |

# 16. Expected Results

- The multi-modal fusion model will outperform tumor-only models, achieving a C-index > 0.65 on held-out TCGA data.

- Dysregulation features will add independent prognostic value beyond raw expression.

- Immune features will partially mediate the effect of dysregulation on survival — patients with high dysregulation and low immune infiltration will have the worst outcomes.

- SHAP analysis will identify 20–50 biologically interpretable genes/immune features as key drivers.

- External validation in GEO and CPTAC will confirm top findings with comparable C-index.

# 17. Possible Risks & Challenges

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| TCGA and GTEx batch effects confound dysregulation scores | Medium | Use careful normalization (ComBat-seq); check PCA for batch clustering |
| CIBERSORT returns poor fractions on bulk RNA-seq | Low-Medium | Use TIMER2.0 or quanTIseq as alternatives; compare methods |
| Fusion model overfits small LUAD cohort (~500 samples) | Medium | Strong regularization (dropout, L2); cross-validate; use simpler architectures first |
| GEO cohort uses different expression platforms (microarray) | Medium | Use platform-appropriate normalization; validate only overlapping features |
| C-index improvement is modest and may not be statistically significant | Medium | Report confidence intervals; frame as proof-of-concept; still publishable |
| Model is uninterpretable and SHAP fails to reveal biology | Low | Start with simpler Cox-Lasso whose coefficients are directly interpretable |

# 18. Backup Plans

- If multi-modal fusion overfits: fall back to Cox-Lasso with concatenated features — this is still a valid contribution with good interpretability.

- If CIBERSORT fails: use xCell or quanTIseq (both R-based, no server submission required).

- If GTEx batch effects are unresolvable: use TCGA matched normals (available for ~50 LUAD patients) as the healthy reference instead.

- If GEO cohort is incompatible: use a second split of TCGA as pseudo-external validation with clearly stated limitations.

- If deep learning adds no value over Cox-Lasso: the dysregulation + immune feature paper is still publishable — the biological finding is the core contribution, not the architecture.

# 19. What Would Make This Publishable

Minimum publishable unit: A clear demonstration that dysregulation scores add independent prognostic value over tumor expression alone, in LUAD, with at least one external validation cohort and biologically interpretable SHAP features. This alone is sufficient for a solid methods/bioinformatics paper.

What would make it a stronger paper: Multi-modal fusion model outperforming all baselines + external validation in two cohorts + SHAP-derived gene signature validated in literature + mechanistic story linking dysregulation → immune evasion → poor survival. This would be suitable for Briefings in Bioinformatics or PLOS Computational Biology.

20. Suggested Figures & Diagrams

| Figure | Description | Tool |
| --- | --- | --- |
| Fig 1 — Study Design Schematic | Visual overview of the 4 data streams and model architecture | BioRender / PowerPoint |
| Fig 2 — Dysregulation Score Distribution | Heatmap of top 100 dysregulated genes across patients; PCA colored by survival | ggplot2 (R) |
| Fig 3 — Immune Landscape | Stacked bar chart of CIBERSORT fractions per patient; correlation heatmap with dysregulation | ggplot2 (R) |
| Fig 4 — Survival Curves (KM) | Kaplan-Meier curves stratifying patients by dysregulation high/low and immune high/low | survminer (R) |
| Fig 5 — Model Comparison | Bar plot of C-index ± CI for all 6 models across training, test, and validation sets | matplotlib (Python) |
| Fig 6 — SHAP Summary Plot | Beeswarm SHAP plot for top 30 features in the best model | shap library (Python) |
| Fig 7 — Biological Interpretation | Pathway enrichment of top SHAP genes; network visualization | clusterProfiler + ggplot2 |
| Fig 8 — External Validation | C-index and AUC comparison across TCGA, GEO, CPTAC | matplotlib (Python) |

# 21. Baseline Models Before Deep Learning

Always start simple. These baselines must be run and reported before any deep learning model. If the deep learning model does not beat these, it is not worth using.

- Baseline 1 — Clinical Cox: age, sex, smoking status, TNM stage. This is the clinical standard of care benchmark.

- Baseline 2 — Expression Cox-Lasso: top expression features selected by Lasso penalty.

- Baseline 3 — Dysregulation Cox-Lasso: dysregulation z-scores as input to Lasso Cox.

- Baseline 4 — Immune Cox-Lasso: CIBERSORT fractions + ssGSEA scores as input.

- Baseline 5 — Concatenated Cox-Lasso: all features combined in one Cox-Lasso model (strong baseline for deep learning to beat).

Only after all 5 baselines are benchmarked should the DeepSurv and fusion models be introduced. This is both scientifically rigorous and practically protective — if deep learning underperforms, you still have a complete paper.

# 22. Final Expected Deliverables

| Deliverable | Format | Owner |
| --- | --- | --- |
| Cleaned TCGA-LUAD + GTEx expression matrices | CSV / RDS files | Biology Student |
| Dysregulation z-score matrix (patients × genes) | CSV / RDS | Biology Student |
| Immune cell fraction matrix (CIBERSORT + ssGSEA) | CSV / RDS | Biology Student |
| Cox-Lasso baseline model results | HTML/PDF report (R Markdown) | Biology Student |
| Multi-modal PyTorch model code | GitHub repository | ML Student (Parth) |
| Full model performance comparison table | CSV + figure | ML Student (Parth) |
| SHAP feature importance analysis | CSV + figure | ML Student (Parth) |
| External validation results (GEO + CPTAC) | CSV + figure | Both |
| Complete figures (8 publication-ready) | PDF / SVG | Both |
| Research paper draft | LaTeX / Word | Both |
| GitHub repository with reproducible pipeline | Public GitHub | Both |

# Project Story — The Scientific Contribution in Plain Language

The One-Paragraph Summary: Lung adenocarcinoma kills more people than any other cancer subtype, yet we still cannot reliably predict which patients will survive. Current computational models stare at the tumor and ask 'what genes are active?' — but they fail to ask 'how far has this cell drifted from what a healthy lung cell should look like?' and 'how is the immune system responding to that drift?' This project answers both questions simultaneously. We will compute, for every patient, a molecular drift score — how much each gene has deviated from healthy lung tissue — and combine it with the immune landscape of the tumor using a multi-modal machine learning model. We will show that this combination predicts survival better than tumor expression alone, identify which drifted genes and immune features matter most, and validate our findings in two independent patient cohorts. The result is not just a better model — it is a biological story: tumors that have drifted far from normal, but evade immune detection, are the ones that kill patients fastest.

| Aspect | This Project's Answer |
| --- | --- |
| Scientific question | Does tumor-normal deviation + immune profile predict LUAD survival better than expression alone? |
| Key novelty | Dysregulation score (tumor vs healthy lung) as a structured, patient-specific input feature |
| ML contribution | Multi-modal fusion survival model with stream-level attention and SHAP interpretability |
| Biological contribution | Identification of deviation-immune interaction genes as survival biomarkers |
| Validation strategy | Internal 20% hold-out + GEO external cohort + CPTAC independent cohort |
| Target journal | Briefings in Bioinformatics / PLOS Computational Biology |
| Realistic timeline | 6 weeks to working models; 2 additional weeks for writing |

— End of Research Proposal —

GOOD LUCK TO US